## Cover Page
Personal Finance Tracker
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Arijit Kumar Haldar
| Role | CSD Intern
Signature
Date
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog Personal Finance Tracker Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | Create database and Tables | 8
Task_1 | Create login table |  | Arijit Kumar Haldar | Completed | 2 | 2 | 0 | 0 | 0 | 0
Task_2 | Create income table |  | Arijit Kumar Haldar | Completed | 2 | 1 | 1 | 0 | 0 | 0
Task_3 | Create expenditure table |  | Arijit Kumar Haldar | Completed | 2 | 0 | 1 | 1 | 0 | 0
Task_4 | Create expenditure category table |  | Arijit Kumar Haldar | Completed | 2 | 0 | 0 | 1 | 1 | 0
User Story #2 | Design POJO classes in Java | 5
Task_1 | Design Login POJO class |  | Arijit Kumar Haldar | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task_2 | Design Income POJO class |  | Arijit Kumar Haldar | Completed | 1 | 0 | 1 | 0 | 0 | 0
Task_3 | Design Expenditure POJO class |  | Arijit Kumar Haldar | Completed | 1 | 0 | 0 | 1 | 0 | 0
Task_4 | Design Expenditure Category POJO class |  | Arijit Kumar Haldar | Completed | 2 | 0 | 0 | 1 | 1 | 0
User Story #3 | Use Spring JDBC to test CRUD operations | 8
Task_1 | Implement Login DAO |  | Arijit Kumar Haldar | Completed | 2 | 2 | 0 | 0 | 0 | 0
Task_2 | Implement Income DAO |  | Arijit Kumar Haldar | Completed | 2 | 0 | 2 | 0 | 0 | 0
Task_3 | Implement Expenditure DAO |  | Arijit Kumar Haldar | Completed | 2 | 0 | 0 | 2 | 0 | 0
Task_4 | Implement Expenditure Category DAO |  | Arijit Kumar Haldar | Completed | 2 | 0 | 0 | 0 | 2 | 0
User Story #4 | Data Validation | 8
Task_1 | Validate if email id is valid or not |  | Arijit Kumar Haldar | Completed | 2 | 1 | 0 | 0.5 | 0.5 | 0
Task_2 | If email id is valid, then generate user id |  | Arijit Kumar Haldar | Completed | 5 | 2 | 0.5 | 1 | 0.5 | 1
Task_3 | If email id not valid, throw an error |  | Arijit Kumar Haldar | Completed | 6 | 1 | 0 | 3 | 1 | 1
Task_4 | Use the generated user id as user identifier in other tables |  | Arijit Kumar Haldar | Completed | 4 | 0 | 1 | 1.5 | 0 | 1.5
User Story #5 | Testing using Junit | 6
Task_1 | Tested methods for Login |  | Arijit Kumar Haldar | Completed | 2 | 0 | 0 | 1 | 0 | 1
Task_2 | Tested methods for Income |  | Arijit Kumar Haldar | Completed | 6 | 2 | 1 | 0.5 | 1.5 | 1
Task_3 | Tested methods for Expenditure |  | Arijit Kumar Haldar | Completed | 7 | 1.5 | 1.5 | 0 | 2 | 2
Task_4 | Tested methods for Category |  | Arijit Kumar Haldar | Completed | 6 | 2 | 0 | 1 | 2 | 1
TOTAL |  |  |  |  | 59 | 15.5 | 9 | 14.5 | 11.5 | 8.5

## Sprint -2
Sprint Backlog Personal Finance Tracker Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | Switch to JPA | 5
Task_1 | Update pom.xml to include JPA |  | Arijit Kumar Haldar | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task_2 | Create EntityManagerFactory |  | Arijit Kumar Haldar | Completed | 1 | 0 | 1 | 0 | 0 | 0
Task_3 | Replace Spring JDBC DAOs with JPA repositories |  | Arijit Kumar Haldar | Completed | 1 | 0 | 0 | 1 | 0 | 0
Task_4 | Replace CrudRepository with JpaRepository |  | Arijit Kumar Haldar | Completed | 2 | 0 | 1 | 1 | 0 | 0
User Story #2 | Make REST controllers | 6
Task_1 | Design REST controller for Login service |  | Arijit Kumar Haldar | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task_2 | Design REST controller for Income service |  | Arijit Kumar Haldar | Completed | 2 | 0.5 | 0.5 | 0 | 1 | 0
Task_3 | Design REST controller for Expenditure service |  | Arijit Kumar Haldar | Completed | 2 | 0 | 0.5 | 0 | 0 | 1.5
Task_4 | Design REST controller for Category Service |  | Arijit Kumar Haldar | Completed | 1 | 0 | 0 | 0.5 | 0 | 0.5
User Story #3 | Service Layer Testing | 8
Task_1 | Make unit tests for Login service using Mockito |  | Arijit Kumar Haldar | Completed | 3 | 2 | 1 | 0 | 0 | 0
Task_2 | Make unit tests for Income service using Mockito |  | Arijit Kumar Haldar | Completed | 5 | 2 | 2 | 0 | 0.5 | 0.5
Task_3 | Make unit tests for Expenditure service using Mockito |  | Arijit Kumar Haldar | Completed | 5 | 1 | 2 | 0 | 1 | 1
Task_4 | Make unit tests for Category service using Mockito |  | Arijit Kumar Haldar | Completed | 1 | 0 | 0 | 1 | 0 | 0
User Story #4 | API Testing | 6
Task_1 | Test controller APIs using Postman |  | Arijit Kumar Haldar | Completed | 2 | 1 | 1 | 0 | 0 | 0
Task_2 | Add Swagger to the project for API documentation |  | Arijit Kumar Haldar | Completed | 6 | 2 | 1 | 2 | 1 | 0
Task_3 | Describe each versioned APIs in the controller layer |  | Arijit Kumar Haldar | Completed | 1 | 0.5 | 0 | 0.5 | 0 | 0
Task_4 | Perform crud operations and test values on database |  | Arijit Kumar Haldar | Completed | 4 | 1 | 1 | 1 | 1 | 0
User Story #5 | Controller Testing | 8
Task_1 | Make unit tests for Login controller using MockMVC |  | Arijit Kumar Haldar | In-Progress | 4 | 1 | 0 | 2 | 0.5
Task_2 | Make unit tests for Income controller using MockMVC |  | Arijit Kumar Haldar | In-Progress | 6 | 2 | 1 | 1 | 1
Task_3 | Make unit tests for Expenditure controller using MockMVC |  | Arijit Kumar Haldar | In-Progress | 7 | 3 | 2 | 0 | 1
Task_4 | Make unit tests for Category controller using MockMVC |  | Arijit Kumar Haldar | Completed | 3 | 1 | 1 | 1 | 0 | 0
TOTAL |  |  |  |  | 58 | 19 | 15 | 11 | 7 | 3.5

## Data (hidden)
In-Progress
Completed
N/A