## Cover Page
Personal Finance Tracker
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Arijit Kumar Haldar
| Role | CSD Intern
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Personal Finance Tracker Project ID: MDU23CSDAJ004 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
User Story #1 | Create database and Tables | Arijit Kumar Haldar
Task_1 | Create login table |  | Create Login entity and map with login table | Completed | Sprint-1 | 1 | Yes | Yes | Yes | 1
Task_2 | Create income table |  | Create Income entity and map with income table | Completed | Sprint-1 | 2 | Yes | Yes | Yes | 2
Task_3 | Create expenditure table |  | Create Expenditure entity and map with expenditure table | Completed | Sprint-1 | 3 | Yes | Yes | Yes | 3
Task_4 | Create expenditure category table |  | Create Category entity and map with category table | Completed | Sprint-1 | 5 | Yes | Yes | Yes | 5
User Story #2 | Design POJO classes in Java | Arijit Kumar Haldar
Task_1 | Design Login POJO class |  | Make a Login Java class for the login table | Completed | Sprint-1 | 1 | Yes | Yes | Yes | 1
Task_2 | Design Income POJO class |  | Make a Income Java class for the income table | Completed | Sprint-1 | 2 | Yes | Yes | Yes | 2
Task_3 | Design Expenditure POJO class |  | Make a Expenditure Java class for the expenditure table | Completed | Sprint-1 | 3 | Yes | Yes | Yes | 3
Task_4 | Design Expenditure Category POJO class |  | Make a Category Java class for the category table | Completed | Sprint-1 | 5 | Yes | Yes | Yes | 5
User Story #3 | Use Spring JDBC to test CRUD operations | Arijit Kumar Haldar
Task_1 | Implement Login DAO |  | Create Data Access Object layer for Login class | Completed | Sprint-1 | 1 | Yes | Yes | Yes | 1
Task_2 | Implement Income DAO |  | Create Data Access Object layer for Income class | Completed | Sprint-1 | 2 | Yes | Yes | Yes | 2
Task_3 | Implement Expenditure DAO |  | Create Data Access Object layer for Expenditure class | Completed | Sprint-1 | 3 | Yes | Yes | Yes | 3
Task_4 | Implement Expenditure Category DAO |  | Create Data Access Object layer for Category class | Completed | Sprint-1 | 5 | Yes | Yes | Yes | 5
User Story #4 | Data Validation | Arijit Kumar Haldar
Task_1 | Validate if email id is valid or not |  | Regex match email Id to generic mail format | Completed | Sprint-1 | 1 | Yes | Yes | Yes | 1
Task_2 | If email id is valid, then generate user id |  | Generate user id using email id and timestamp | Completed | Sprint-1 | 2 | Yes | Yes | Yes | 2
Task_3 | If email id is not valid, throw an error |  | Handle custom exception | Completed | Sprint-1 | 3 | Yes | Yes | Yes | 3
Task_4 | Use the generated user id as user identifier in other tables |  | Make the generated user id as foreign key | Completed | Sprint-1 | 5 | Yes | Yes | Yes | 5
User Story #5 | Testing using Junit | Arijit Kumar Haldar
Task_1 | Tested methods for Login |  | Write Junit 5 tests for Login DAO | Completed | Sprint-1 | 1 | Yes | Yes | Yes | 1
Task_2 | Tested methods for Income |  | Write Junit 5 tests for Income DAO | Completed | Sprint-1 | 2 | Yes | Yes | Yes | 2
Task_3 | Tested methods for Expenditure |  | Write Junit 5 tests for Expenditure DAO | Completed | Sprint-1 | 3 | Yes | Yes | Yes | 3
Task_4 | Tested methods for Category |  | Write Junit 5 tests for Login DAO | Completed | Sprint-1 | 5 | Yes | Yes | Yes | 5
User Story #6 | Switch to JPA | Arijit Kumar Haldar
Task_1 | Update pom.xml to include JPA |  | Add additional depedencies | Completed | Sprint-2 | 1 | Yes | Yes | Yes | 1
Task_2 | Create EntityManagerFactory |  | Call entity manager factory class to define crud operations | Completed | Sprint-2 | 2 | Yes | Yes | Yes | 2
Task_3 | Replace Spring JDBC DAOs with JPA repositories |  | Make repository interfaces | Completed | Sprint-2 | 3 | Yes | Yes | Yes | 3
Task_4 | Replace CrudRepository with JpaRepository |  | Use JpaRepository to extend the interfaces | Completed | Sprint-2 | 5 | Yes | Yes | Yes | 5
User Story #7 | Make REST controllers | Arijit Kumar Haldar
Task_1 | Design REST controller for Login service |  | Make login controller | Completed | Sprint-2 | 1 | Yes | Yes | Yes | 1
Task_2 | Design REST controller for Income service |  | Make income controller | Completed | Sprint-2 | 2 | Yes | Yes | Yes | 2
Task_3 | Design REST controller for Expenditure service |  | Make expenditure controller | Completed | Sprint-2 | 3 | Yes | Yes | Yes | 3
Task_4 | Design REST controller for Category Service |  | Make category controller | Completed | Sprint-2 | 5 | Yes | Yes | Yes | 5
User Story #8 | Service Layer Testing | Arijit Kumar Haldar
Task_1 | Make unit tests for Login service using Mockito |  | Write Junit tests for Login service implementation | Completed | Sprint-2 | 1 | Yes | Yes | Yes | 1
Task_2 | Make unit tests for Income service using Mockito |  | Write Junit tests for Income service implementation | Completed | Sprint-2 | 2 | Yes | Yes | Yes | 2
Task_3 | Make unit tests for Expenditure service using Mockito |  | Write Junit tests for Expenditure service implementation | Completed | Sprint-2 | 3 | Yes | Yes | Yes | 3
Task_4 | Make unit tests for Category service using Mockito |  | Write Junit tests for Category service implementation | Completed | Sprint-2 | 5 | Yes | Yes | Yes | 5
User Story #9 | API Testing | Arijit Kumar Haldar
Task_1 | Test controller APIs using Postman |  | Try out crud operations using postman | Completed | Sprint-2 | 1 | Yes | Yes | Yes | 1
Task_2 | Add Swagger |  | Add Swagger to the project for API documentation | Completed | Sprint-2 | 2 | Yes | Yes | Yes | 2
Task_3 | Describe each versioned APIs in the controller layer |  | Make API documentation for Swagger | Completed | Sprint-2 | 3 | Yes | Yes | Yes | 3
Task_4 | Perform crud operations and test values on database |  | Test out the mappings done for any errors | Completed | Sprint-2 | 5 | Yes | Yes | Yes | 5
User Story #10 | Controller Testing | Arijit Kumar Haldar
Task_1 | Make unit tests for Login controller using MockMVC |  | Write Junit tests for Login controller | Completed | Sprint-2 | 1 | Yes | Yes | Yes | 1
Task_2 | Make unit tests for Income controller using MockMVC |  | Write Junit tests for Income controller | Completed | Sprint-2 | 2 | Yes | Yes | Yes | 2
Task_3 | Make unit tests for Expenditure controller using MockMVC |  | Write Junit tests for Expenditure controller | Completed | Sprint-2 | 3 | Yes | Yes | Yes | 3
Task_4 | Make unit tests for Category controller using MockMVC |  | Write Junit tests for Category controller | Completed | Sprint-2 | 5 | Yes | Yes | Yes | 5

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000